## All Drivers
driver_name | asset_id | job_site | scheduled_start | scheduled_end | actual_start | actual_end | status | status_reason | identity_verified | employee_id | identity_source
Christopher Thomas | TRK-1011 | Downtown Construction | 06:30 AM | 03:30 PM | 06:29 AM | 03:33 PM | On Time |  | TRUE | E1011 | employee_master_list.csv
John Smith | TRK-1001 | North Dallas Site | 06:30 AM | 03:30 PM | 06:25 AM | 03:35 PM | On Time |  | TRUE | E1001 | employee_master_list.csv
James Davis | TRK-1005 | North Dallas Site | 06:00 AM | 03:00 PM | 07:03 AM | 03:12 PM | Not On Job | At incorrect location: North Richland Hills | TRUE | E1005 | employee_master_list.csv
Anthony Martin | TRK-1014 | West Plano Project | 07:00 AM | 04:00 PM | 07:16 AM | 03:58 PM | Late | 16 minutes late | TRUE | E1014 | employee_master_list.csv
Mark Thompson | TRK-1015 | Downtown Construction | 06:00 AM | 03:00 PM | N/A | N/A | On Time |  | TRUE | E1015 | employee_master_list.csv
David Miller | TRK-1006 | West Plano Project | 06:45 AM | 03:45 PM | 06:47 AM | 03:42 PM | On Time |  | TRUE | E1006 | employee_master_list.csv
Matthew Harris | TRK-1013 | North Dallas Site | 06:45 AM | 03:45 PM | 06:52 AM | 03:37 PM | On Time |  | TRUE | E1013 | employee_master_list.csv
William Brown | TRK-1004 | Richardson Development | 06:30 AM | 03:30 PM | 06:32 AM | 02:54 PM | Early End | 36 minutes early | TRUE | E1004 | employee_master_list.csv
Michael Johnson | TRK-1002 | West Plano Project | 06:00 AM | 03:00 PM | 06:18 AM | 03:07 PM | Late | 18 minutes late | TRUE | E1002 | employee_master_list.csv
Robert Williams | TRK-1003 | Downtown Construction | 07:00 AM | 04:00 PM | 07:28 AM | 03:45 PM | Late | 28 minutes late | TRUE | E1003 | employee_master_list.csv
Charles Anderson | TRK-1010 | West Plano Project | 06:00 AM | 03:00 PM | 06:05 AM | 02:48 PM | On Time |  | TRUE | E1010 | employee_master_list.csv
Thomas Taylor | TRK-1009 | North Dallas Site | 07:00 AM | 04:00 PM | 06:43 AM | 03:52 PM | On Time |  | TRUE | E1009 | employee_master_list.csv
Richard Wilson | TRK-1007 | Downtown Construction | 06:15 AM | 03:15 PM | 06:14 AM | 03:18 PM | On Time |  | TRUE | E1007 | employee_master_list.csv
Daniel Jackson | TRK-1012 | Richardson Development | 06:15 AM | 03:15 PM | 06:16 AM | 03:12 PM | On Time |  | TRUE | E1012 | employee_master_list.csv
Joseph Moore | TRK-1008 | Richardson Development | 06:30 AM | 03:30 PM | 06:55 AM | 03:25 PM | Late | 25 minutes late | TRUE | E1008 | employee_master_list.csv

## On Time
driver_name | asset_id | job_site | scheduled_start | scheduled_end | actual_start | actual_end | status | status_reason | identity_verified | employee_id | identity_source
Christopher Thomas | TRK-1011 | Downtown Construction | 06:30 AM | 03:30 PM | 06:29 AM | 03:33 PM | On Time |  | TRUE | E1011 | employee_master_list.csv
John Smith | TRK-1001 | North Dallas Site | 06:30 AM | 03:30 PM | 06:25 AM | 03:35 PM | On Time |  | TRUE | E1001 | employee_master_list.csv
Mark Thompson | TRK-1015 | Downtown Construction | 06:00 AM | 03:00 PM | N/A | N/A | On Time |  | TRUE | E1015 | employee_master_list.csv
David Miller | TRK-1006 | West Plano Project | 06:45 AM | 03:45 PM | 06:47 AM | 03:42 PM | On Time |  | TRUE | E1006 | employee_master_list.csv
Matthew Harris | TRK-1013 | North Dallas Site | 06:45 AM | 03:45 PM | 06:52 AM | 03:37 PM | On Time |  | TRUE | E1013 | employee_master_list.csv
Charles Anderson | TRK-1010 | West Plano Project | 06:00 AM | 03:00 PM | 06:05 AM | 02:48 PM | On Time |  | TRUE | E1010 | employee_master_list.csv
Thomas Taylor | TRK-1009 | North Dallas Site | 07:00 AM | 04:00 PM | 06:43 AM | 03:52 PM | On Time |  | TRUE | E1009 | employee_master_list.csv
Richard Wilson | TRK-1007 | Downtown Construction | 06:15 AM | 03:15 PM | 06:14 AM | 03:18 PM | On Time |  | TRUE | E1007 | employee_master_list.csv
Daniel Jackson | TRK-1012 | Richardson Development | 06:15 AM | 03:15 PM | 06:16 AM | 03:12 PM | On Time |  | TRUE | E1012 | employee_master_list.csv

## Late
driver_name | asset_id | job_site | scheduled_start | scheduled_end | actual_start | actual_end | status | status_reason | identity_verified | employee_id | identity_source
Anthony Martin | TRK-1014 | West Plano Project | 07:00 AM | 04:00 PM | 07:16 AM | 03:58 PM | Late | 16 minutes late | TRUE | E1014 | employee_master_list.csv
Michael Johnson | TRK-1002 | West Plano Project | 06:00 AM | 03:00 PM | 06:18 AM | 03:07 PM | Late | 18 minutes late | TRUE | E1002 | employee_master_list.csv
Robert Williams | TRK-1003 | Downtown Construction | 07:00 AM | 04:00 PM | 07:28 AM | 03:45 PM | Late | 28 minutes late | TRUE | E1003 | employee_master_list.csv
Joseph Moore | TRK-1008 | Richardson Development | 06:30 AM | 03:30 PM | 06:55 AM | 03:25 PM | Late | 25 minutes late | TRUE | E1008 | employee_master_list.csv

## Early End
driver_name | asset_id | job_site | scheduled_start | scheduled_end | actual_start | actual_end | status | status_reason | identity_verified | employee_id | identity_source
William Brown | TRK-1004 | Richardson Development | 06:30 AM | 03:30 PM | 06:32 AM | 02:54 PM | Early End | 36 minutes early | TRUE | E1004 | employee_master_list.csv

## Not On Job
driver_name | asset_id | job_site | scheduled_start | scheduled_end | actual_start | actual_end | status | status_reason | identity_verified | employee_id | identity_source
James Davis | TRK-1005 | North Dallas Site | 06:00 AM | 03:00 PM | 07:03 AM | 03:12 PM | Not On Job | At incorrect location: North Richland Hills | TRUE | E1005 | employee_master_list.csv

## Verification
Metric | Value
Total Drivers (Original) | 15
Verified Drivers | 15
Unverified Drivers | 0
Ghost Drivers | 0
Identity Match Rate | 100.0%
Verification Source | Equipment Billing Master (186 drivers)